## Procurement Register
Reference | Description of Procurement | Directorate | Process | Process Release Date | Closing Date | Contractor Name | State | Territory Enterprise (Y or N) | Contract Award Date | Contract Award ($) GST inclusive
2018
BRC 001-18 | Repair of Alpurrurulam Roads | Infrastructure | Request for Tender | First released on 11/05/2018. Re-advertised on 31/07/2018 | 8/06/2018. New closing date of re-advertised tender on 31/08/2018 | Remote Civil PTY LTD | NT | Y | 2018-11-18 | 589819.56
BRC 002-18 | Design and Construct Elliott Footy Oval | Infrastructure | Request for Tender | First released on 8/06/2018. Re-advertised on 10/10/2018 | 10/09/2018. New closing date of re-advertised tender on 31/10/2018 | Arnhem Earthmoving and Mechanical PTY LTD | NT | Y | 2018-12-24 | 937065.71
BRC 004-18 | COLA Shelter over Existing Ali Curung Basketball Court | Infrastructure | Request for Tender | 2018-07-31 | 2018-08-24 | Harvey Developments PTY LTD | NT | Y | 2018-10-04 | 216700
2019
BRC 001-19 | Design and Construct a COLA Shelter over existing Wutunugurra Basketball Court | Infrastructure | Request for Tender | 2019-09-22 | 2019-03-18 | Harvey Developments PTY LTD | NT | Y | 2019-04-26 | 212541.63
BRC 002-19 | Design and Construction of HVAC Cooling System for Tennant Creek Civic Hall | Barkly Regional Council | Request for Tender | 2019-03-15 | 2019-04-10 | Emperor Refrigeration PTY LTD | NT | Y | 2019-08-07 | 324511
BRC 003-19 | Supply and Construct New Fence at Alpurrurulam Landfill | Infrastructure | Request for Tender | 2019-12-18 | 2019-01-13 | Hardy Fencing | NT | Y | 2020-08-05 | 156235.42
BRC 004-19 | Supply LED Street Lights to Tennant Creek | Operations | Request for Tender | 2019-12-18 | 2020-01-31 | MM Electrical Merchandising | NT | Y | 2020-09-08 | 188871.66
2020
BRC 001-20 | Demolition of Existing Skate Park and Installation of New Skate Park in Alpurrurulam | Infrastructure | Request for Tender | 2020-01-29 | 2020-03-06 | Remote Concrete NT | NT | Y | 2020-06-30 | 222508
BRC 002-20 | Survey and Engineering Design of Bicycle Path at Tennant Creek | Infrastructure | Request for Tender | 2020-02-03 | 2020-03-16 | FYFE PTY LTD | NT | Y | 2021-01-31 | 222508
BRC 004-20 | Supply and Construct New Fence at Alpurrurulam Landfill | Infrastructure | Request for Tender | First released on 18/12/2019. Re-advertised tender on 9/07/2020 | 13/01/2020. New closing date of re-advertised tender on 24/07/2020 | Hardy Fencing NT | NT | Y | 2020-08-05 | 156235.42
BRC 005-20 | Testing, Inspection and Repair of Fire Extinguishing Equipment in Barkly Buildings and Facilities in Tennant Creek and Communities | Barkly Regional Council | Request for Tender | 2020-05-19 | 2020-06-22 | Ronin Security Technologies | NT | Y | 2020-10-30 | 49500
BRC 005-20 | Elliott Oval Change Rooms | Infrastructure | Request for Tender | 2020-09-25 | 2020-10-22 | Harvey Developments PTY LTD | NT | Y | 2020-12-07 | 618766.95
BRC 006-20 | Ampilatwatja Ablution Block | Infrastructure | Request for Tender | 2020-09-25 | 2020-10-22 | Harvey Developments PTY LTD | NT | Y | 2020-12-07 | 533361.32
BRC 007-20 | Lake Mary Ann Playground | Community Services | Request for Tender | 2020-10-01 | 2020-10-29 | NT Sports and Playground Surfacing | NT | Y | 2020-11-27 | 383317
BRC 008-20 | Design and Construct Tennant Creek Cemetery Chapel | Infrastructure | Request for Tender | 2020-12-08 | 2021-01-14 | Harvey Developments PTY LTD | NT | Y | 2021-02-02 | 541035.61
BRC 009-20 | Design and Construct Ali Curung Youth Centre | Infrastructure | Request for Tender | 2020-12-18 | 2021-01-28 | Harvey Developments PTY LTD | NT | Y | 2021-02-22 | 2559828.09
BRC 2020 Civil/001 | Ampilatwatja Bitumen Reseal and Decompaction | Infrastructure | Request for Tender |  | 2020-10-13 | NT Bitumen & Asphalt PTY LTD | NT | Y | 2020-11-06 | 588766.77
BRC 2020 Civil/002 | Bitumen Reseal Tennant Creek Town Streets | Infrastructure | Request for Tender | 2020-10-28 | 2020-11-25 | F & J Bitumen Services | NT | Y | 2021-02-11 | 406066.5
BRC-0820-01 | Fire Protection and Detection System Servicing for Twelve (12) Months | Barkly Regional Council | Request for Tender |  | 2020-06-22 | Ronin Security Technologies | NT | Y |  | 85901.8
BRC YCT-0100 | Design and Construct Tennant Creek Youth Centre | Infrastructure | Request for Tender | 2020-07-27 | 2020-09-07 | Remote Industries Australia. Includes the supply and installation of the Ninja Course by the Highgate Group (NSW). | NT | Y | 2021-04-15 | 3196050
| Supply and Delivery of One (1) JCB 535-95C Telehandler | Operations | Request for Quotation | 2019-11-27 | 2019-12-04 | Construction Equipment Australia (CEA/JCB) | SA | N | 2020-01-30 | 133470
BRC 2020-RFQ-001 | Supply and Delivery of One (1) Diesel 8T Payload Truck with 8.0 Litre Water Tank | Operations | Request for Quotation | 2020-07-24 | 2020-08-19 | Winter & Taylor Motor Group | VIC | N | 2020-10-07 | 163169.2
BRC 2020-RFQ-002 | Supply and Delivery of Three (3) Utility Vehicles | Operations | Request for Quotation | 2020-08-07 | 2020-09-04 | No Successful Tenderer.
BRC 2020-RFQ-003 | Supply and Delivery of One (1) Ford Ranger Vehicle | Administration | Request for Quotation | 2020-08-21 | 2020-08-31 | The Trustee for Centralian Motors Unit | NT | Y | 2020-10-15 | 48526.09
BRC 2020-RFQ-004 | Supply and Delivery of One (1) Backhoe Loader | Operations | Request for Quotation | 2020-11-23 | 2020-12-11 | Forklift Solutions PTY LTD | NT | Y | 2021-02-18 | 168729
BRC 2020-RFQ-005 | Supply and Delivery of One (1) 4.5 Tonne Crew Cab Tipper for Tennant Creek | Operations | Request for Quotation | 2020-12-11 | 2020-12-30 | Heath Motor Group PTY LTD | NT | Y | 2021-02-03 | 85243.81
BRC 2020-RFQ-006 | Supply and Delivery of One (1) 6 Tonne Single Cab Tipper for Elliott | Operations | Request for Quotation | 2020-12-11 | 2020-12-30 | Heath Motor Group PTY LTD | NT | Y | 2021-02-03 | 104783.86
BRC 2020-RFQ-007 | Supply and Delivery of Three (3) Toyota Hilux Vehicles | Night Patrol Community Services | Request for Quotation | 2021-01-08 | 2021-01-29 | Peter Kittle Alice Springs | NT | Y | 2021-02-24 | 213113.35
| Supply Two (2) Skidsteers on Trailers | Operations | Request for Quotation | 2020-05-15 | 2020-05-22 | RDO Equipment PTY LTD | NT | Y | 2020-06-04 | 246000
| Workplace Mentoring and Skills Development Program | People and Culture | Expressions of Interest | 2020-08-13 | 2020-08-28 | Central Desert Training PTY LTD | NT | Y | 2020-10-02 | 194730.14
2021
BRC 001-21 | Design and Construct Ampilatwatja Sports and Recreation Centre | Infrastructure | Request for Tender | 2021-01-29 | 2021-02-25 | Harvey Developments PTY LTD | NT | Y | 2021-03-31 | 811529.62
BRC 002-21 | Design and Construct BMX Track in Wutunugurra | Infrastructure | Request for Tender | 2021-01-29 | 2021-02-25 | Bennally PTY LTD | NT | Y | 2021-03-31 | 97328
BRC 003-21 | Design and Construct Basketball Court in Alpurrurulam | Infrastructure | Request for Tender | 2021-01-29 | 2021-02-25 | NT Sports and Playground Surfacing PTY LTD | NT | Y | 2021-03-31 | 256999.6
BRC 004-21 | Refurbishment and Associated Works at Arlparra Sports and Recreation Centre | Infrastructure | Request for Tender | 2021-02-16 | 2021-03-09 | Complete Constructions NT PTY LTD | NT | Y | 2021-03-31 | 150630.48
BRC 005-21 | Supply and Installation of Demountable Accommodations for Night Patrol | Community Services | Request for Tender | 2021-03-01 | 15/03/2021 Extended to 17/03/2021 | No Successful Tenderer. Under Review.
BRC 006-21 | Wutunugurra Women Art Centre Upgrade | Community Services | Request for Tender | 2021-03-19 | 2021-04-15 | MPH Carpentry and Constructions PTY LTD | NT | Y | 2021-04-30 | 237600
BRC 007-21 | Bitumen Reseal Tennant Creek Town Streets and Elliott (Phase 2) | Infrastructure | Request for Tender | 2021-04-23 | 2021-05-13 | F & J Bitumen Services | NT | Y | 2021-06-24 | 499897.65
BRC 008-21 | Supply and Install Thirteen (13) Sheltered Picnic Tables at Lake Mary Ann | Infrastructure | Request for Tender | 2021-04-29 | 2021-05-13 | Harvey Developments PTY LTD | NT | Y | 2021-06-21 | 135514.51
BRC 009-21 | Supply and Delivery of One (1) Demountable Office for Tennant Creek Landfill | Infrastructure | Request for Tender | 2021-08-05 | 2021-09-02 | MPH Carpentry and Constructions PTY LTD | NT | Y | 2021-09-28 | 120731.6
BRC 010-21 | Supply and Delivery of Two (2) x 10' Class 8 DG Containers for Tennant Creek Swimming Pool | Infrastructure | Request for Tender | 2021-08-05 | 2021-09-02 | MPH Carpentry and Constructions PTY LTD | NT | Y | 2021-09-28 | 108967.1
BRC 2021-RFQ-001 | Supply and Install Thirteen (13) Sheltered Picnic Tables at Lake Mary Ann | Infrastructure | Request for Quotation | 2021-03-15 | 2021-03-26 | No Successful Tenderer. Re-tendered as a Request for Tender. BRC 008-21
BRC 2021-RFQ-002 | Supply and Installation of Pool Covers at the Tennant Creek Swimming Pool | Community Services | Request for Quotation | 2021-06-18 | 2021-07-12 | Pool Covers Australia PTY LTD Trading as Just Covers | NSW | N | 2021-09-13 | 38489
BRC 2021-RFQ-003 | Community Care Training in Remote NT | Community Services | Request for Quotation | 2021-07-30 | 19/08/2021 extended to 02/09/2021 | Response Employment and Training PTY LTD | NT | Y | 2021-12-01 | 164080
BRC 2021-RFQ-004 | Supply and Delivery of Five (5) Ford Rangers DCUTE to Tennant Creek | Community Services | Request for Quotation | 2021-07-26 | 2021-08-02 | Centralian Motors NT PTY LTD-CANCELLED FOR NON-DELIVERY/NON-COMPLIANCE | NT | Y | 2021-08-20 | 246012.85
BRC 2021-RFQ-005 | Supply and Delivery of One (1) 10 Tonne Tipper to Tennant Creek | Operations | Request for Quotation | 2021-09-08 | 2021-09-29 | CJD Equipment PTY LTD | NT | Y | 2022-05-03 | 229856.11
BRC 2021-RFQ006 | Supply and Delivery of One (1) Automated Side-Loading Garbage Truck to Tennant Creek | Operations | Request for Quotation | 2021-10-11 | 2021-10-29 | UNDER ASSESSMENT
BRC 2021-EOI-001 | Community Care Training in Remote NT | Community Services | Expressions of Interest | 2021-02-05 | 2021-03-19 | First Stage of the Tendering Process completed. Issued RFQ BRC 2021-RFQ-003
2022
BRC 2022-EOI-001 | The Juno Project | Barkly Regional Council | Expressions of Interest | 2022-01-12 | 2022-02-11 | FOR ASSESSMENT
BRC 2022-RFQ-001 | Supply Four (4) Toyota Hilux 4 x 4 SR Vehicles | Barkly Regional Council for Community Care | Request for Quotation | 2022-03-30 | 2022-04-19 | FOR ASSESSMENT
RFT BRC001-22 | Tennant Creek Peko Park-Replacement of Fuuly-Automated UNISEX Accessible Compliant WC | Barkly Regional Council | Request for Tender |  |  | FOR COUNCIL RECOMMENDATION AND APPROVAL
RFT BRC002-22 | Tennant Creek Shared Path Construction | Barkly Regional Council | Request for Tender | 2022-03-24 | 2022-04-14 | FOR COUNCIL RECOMMENDATION AND APPROVAL
RFT BRC003-22 | Tennant Creek Lake Mary Ann Public Toilet Upgrade | Barkly Regional Council | Request for Tender | 2022-05-06 | 2022-05-19 | TENDER PROCESS
LEGEND
No information available.
Reference | Marked "red" on repeat tender title number
Contract Award Date | Marked "red" -based on Purchase Order Date.
REFERENCES
(1) Procurement Documents
(2) TechOne Purchase Orders Detail Enquiry
(3) Tenderlink portal
(4) Local Buy Vendor Panel
(5) Public Tender Advertising-NT News Advertising